# MUTOKO RURAL DISTRICT COUNCIL
PRODUCTION IMPLEMENTATION PLAN

React + TypeScript + Inertia.js + Laravel Modular Monolith + FilamentPHP

Theme 1: Modern Civic • Version 1.0 • September 2026

# 1. Purpose and Delivery Principle

This plan converts the approved SRS, production database design, RTM and Theme 1 UI/UX standard into an executable delivery sequence. The website will remain a single Laravel modular monolith. The public experience will use React + TypeScript through Inertia.js; FilamentPHP will provide the internal CMS. Development is stage-gated: a stage is not accepted because code exists; it is accepted only when its required evidence and quality gates pass.

# 2. Locked Technology Baseline

| Layer | Technology | Role |
| --- | --- | --- |
| Application | Laravel 12/13, PHP 8.4+ | Single production application and business-rule authority |
| Public UI | React + TypeScript + Inertia.js | Public council website |
| Build | Vite | Frontend compilation within Laravel |
| Design | Theme 1 + Tailwind CSS | Modern Civic design system |
| CMS | FilamentPHP | Internal administration/content management |
| Database | MySQL 8 | Primary relational persistence |
| Cache/Queue | Redis | Cache, queues, throttling and selected sessions |
| Testing | Pest/PHPUnit, Vitest/RTL, Playwright | Backend, frontend and E2E quality |
| Web | Nginx + HTTPS | Production serving |
| CI/CD | GitHub Actions or GitLab CI | Automated release gates |

# 3. Delivery Architecture

One repository, one Laravel application, one primary MySQL database and one production deployment unit.

React is not a separately deployed SPA. Laravel routes/controllers return Inertia pages and typed props.

Node/Vite is a build-time tool; it is not a permanent production frontend server.

Filament shares the same application/domain services, authorization policies and database.

REST/API endpoints are introduced only for genuine external integrations or future clients.

Modules are internally separated by domain boundaries without introducing microservices.

# 4. Stage-Gated Implementation Roadmap

| Stage | Name | Primary Work | Deliverable | Exit Gate | Status |
| --- | --- | --- | --- | --- | --- |
| Stage 0 | Requirements & Delivery Freeze | Confirm SRS, RTM, Theme 1, architecture, environments, content ownership and acceptance process. | Approved baseline; decision log; backlog; risks; content inventory. | No unresolved P0 architecture/scope decision. | Planned |
| Stage 1 | Production Foundation | Bootstrap Laravel monolith; React/TS/Inertia/Vite/Tailwind; Filament; MySQL; Redis; Git/CI; coding standards; logging; env config; test harnesses. | Running application shell; admin login shell; CI pipeline; health check; baseline tests. | Backend tests, TS check, frontend build, lint/static checks and environment smoke pass. | Planned |
| Stage 2 | Identity, Organisation & Security | Users, roles, permissions, departments, scoped access, policies, authentication hardening, audit events, settings and seeders. | RBAC/security foundation and organisation model. | Positive and negative authorization tests pass; privileged changes audited. | Planned |
| Stage 3 | Data & Content Foundation | Pages, translations, media, documents/versions, categories/tags, SEO metadata, redirects, revisions, approvals. | Production migrations/models/services and CMS foundation. | Fresh migration/seed on MySQL; constraints/indexes verified; persistence tests pass. | Planned |
| Stage 4 | Theme 1 Design System & Public Shell | Implement tokens, typography, header, navigation, mobile menu, breadcrumbs, footer, layouts, primitives and shared civic components. | Responsive React/Inertia website shell and component inventory. | Visual review, keyboard checks, responsive checks and component tests pass. | Planned |
| Stage 5 | Institutional CMS & Public Content | Council profile, leadership, departments, governance, policies/by-laws, financial/public documents and static pages. | Filament management + corresponding React public pages. | Editor workflow and public rendering verified with realistic content. | Planned |
| Stage 6 | Communications | News, notices, events, homepage curation, publication dates, related content and archive behavior. | Communications CMS and public editorial experience. | Draft/review/publish, expiry/archive, SEO and mobile states pass. | Planned |
| Stage 7 | Procurement & Careers | Tenders and vacancies, reference numbers, dates, documents, filters, statuses, automatic closing and archive rules. | Tender/vacancy administration and public listings/detail pages. | Deadline boundary tests and scheduler tests pass; closed items cannot appear open. | Planned |
| Stage 8 | Projects, Investment & Tourism | Projects/development, investment opportunities, tourism/attractions and associated media/content. | Economic-development and destination modules. | Status/content validation, responsive visual QA and permissions pass. | Planned |
| Stage 9 | Engagement, Search & Localization | Contact directory, enquiries, spam controls, site search, English/Shona/Ndebele, language switching and fallback. | Public interaction, discovery and localization. | Search relevance smoke tests; enquiry security; translation/fallback tests pass. | Planned |
| Stage 10 | Governance & Editorial Workflow | Maker/checker approvals, scheduled publication, revision history, scoped ownership and governed changes. | Auditable publication lifecycle. | Unauthorized publish attempts fail; revisions/approvals/audits reconcile. | Planned |
| Stage 11 | SEO, Accessibility & Performance | Sitemap, robots, canonical/meta, structured data where valid, WCAG review, image optimization and Core Web Vitals work. | Discoverability and web-quality hardening. | SEO crawl review; WCAG AA target; agreed performance thresholds pass. | Planned |
| Stage 12 | Full QA, UAT & Security Hardening | Regression, cross-browser, mobile, Playwright journeys, upload security, headers, rate limits, backup/restore and failure handling. | Release candidate and UAT evidence pack. | No Critical/High release defect; critical E2E and security gates pass. | Planned |
| Stage 13 | Production Deployment | Backup, migrations, build artifact, workers, scheduler, SSL, storage, cache, monitoring, smoke and rollback readiness. | Live production website. | Deployment checklist and production smoke tests pass. | Planned |
| Stage 14 | Training, Documentation & Handover | Train administrators/editors; provide guides, runbook, credentials handover process, source and acceptance record. | Operational handover package. | Council sign-off and ownership transfer recorded. | Planned |

# 5. Detailed Work Breakdown

## 5.1 Stage 1 - Foundation

Create repository conventions, branching/review rules and environment templates; never commit secrets.

Install/configure Laravel, React, TypeScript, Inertia.js, Vite and Tailwind.

Install/configure Filament without creating a second application boundary.

Configure MySQL and Redis; establish queue worker and scheduler strategy.

Configure Pest/PHPUnit, Vitest + React Testing Library and Playwright.

Configure code formatting/linting/static analysis appropriate to the stack.

Add structured logging, correlation/request IDs, health endpoint and error handling.

Create modular-monolith namespace/folder conventions and architecture documentation.

Create CI pipeline: dependency install, backend tests, static checks, TS check, frontend tests/build and selected E2E.

## 5.2 Stage 2 - Security Foundation

Implement users, roles, permissions and scoped grants with least privilege.

Implement Laravel policies/authorization at server boundary; UI hiding is not authorization.

Secure Filament access to authorized active users only.

Audit authentication, role/permission changes, publishing, deadlines, settings and sensitive administrative changes.

Add rate limiting, CSRF protection, security headers, upload validation and secure session/cookie configuration.

Define privileged-account controls and MFA readiness/recommendation.

## 5.3 Stages 3-10 - Functional Delivery

Build migrations first with foreign keys, uniqueness, status/date indexes and production-safe constraints.

Implement application/domain actions and policies before coupling behavior to Filament or React.

Build Filament resources around approved workflows and departmental permissions.

Build React/Inertia pages using Theme 1 components and typed props.

Test each module's business rules, negative permissions, boundary dates, empty/error states and mobile behavior.

Maintain RTM linkage from requirement to implementation and verification evidence.

## 5.4 Stages 11-14 - Release Delivery

Run accessibility, SEO, performance, security and regression hardening.

Load/migrate only approved production content and verify links/assets.

Execute UAT with Council representatives and record defects/decisions.

Prepare backup and rollback; deploy under controlled checklist.

Verify queues, scheduler, storage, SSL, redirects, monitoring and production smoke journeys.

Complete training, operating runbook, admin guide and formal handover.

# 6. Theme 1 UI/UX Implementation Stream

Theme 1 - Modern Civic is the design authority. No page may invent a competing visual language.

Implement design tokens before module pages: civic navy, council green, deep green, neutral surfaces, typography, spacing, borders, radii and state colours.

Create shared primitives and civic components before duplicating markup across pages.

Homepage remains task-first: services/quick links, news, tenders, vacancies and development/tourism highlights.

Tenders/documents favor scanability and information density; tourism/investment may use richer imagery while remaining within the same system.

Use authentic, approved Mutoko/council imagery. No fabricated people, projects, metrics or official information.

Every feature must handle real content lengths, missing images, empty data, closed/expired states, errors and translations.

Human visual review is mandatory; passing automated tests alone is not UI acceptance.

# 7. Database Implementation Order

| Wave | Domain | Core tables/aggregates |
| --- | --- | --- |
| Wave 1 | Identity/organisation | users, roles, permissions, user_scopes, departments, site_settings, audit_events |
| Wave 2 | Core content | locales, pages, page_translations, media_assets, documents, document_versions, categories, tags |
| Wave 3 | Governance | content_revisions, approval_requests, approval_steps, seo_metadata, redirects |
| Wave 4 | Communications | posts/news/notices/events and translation/tag relations |
| Wave 5 | Business modules | tenders + documents/translations; vacancies/translations; projects/translations |
| Wave 6 | Promotion | investment opportunities/translations; tourism items/translations |
| Wave 7 | Engagement/operations | contact_points, enquiries, enquiry_events, download_events, jobs/failed_jobs |

# 8. Test Strategy

| Test layer | Coverage |
| --- | --- |
| Unit | Domain rules, value objects/services, status/deadline rules, utilities. |
| Feature/Integration | Routes, actions, persistence, policies, Filament actions, Inertia responses, scheduler/jobs. |
| Database | MySQL migrations, FK/unique/check behavior, indexes, transactions and concurrency where relevant. |
| Frontend | React component behavior, accessibility semantics and state rendering. |
| E2E | Playwright critical journeys on desktop/mobile: navigation, search, tender/vacancy, documents, contact and admin publication. |
| Security | Negative authorization, upload restrictions, validation, rate limiting, headers and privileged operations. |
| Accessibility | Automated checks plus keyboard/focus/manual semantic review. |
| Performance | Production build analysis, images, page behavior and Core Web Vitals on representative pages. |
| UAT | Council-approved scenarios mapped to RTM and signed off. |

# 9. Quality Gates Per Stage

Code compiles/builds cleanly; no knowingly ignored critical build error.

Relevant automated tests pass with evidence.

Static analysis/lint/format checks pass.

Fresh MySQL migration/seed succeeds for database-changing stages.

Authorization includes negative tests, not only happy-path tests.

Responsive/mobile and keyboard behavior reviewed for UI stages.

No fabricated/placeholder production content.

Security-sensitive changes create appropriate audit evidence.

Documentation/RTM updated with the implementation.

No unresolved Critical/High defect before stage acceptance.

# 10. Production Deployment Checklist

Approved release/tag and immutable deployment artifact identified.

Database and uploaded assets backed up; restore path verified.

Production environment/secrets validated without exposing them in source/logs.

Maintenance/rollback procedure agreed.

Composer production install and Vite production build completed.

Database migrations executed and verified.

Storage permissions/symlinks/object storage verified.

Redis, queue workers and scheduler operational.

Nginx, HTTPS, redirects and security headers verified.

Caches warmed/cleared appropriately.

Critical public/admin smoke tests executed.

Monitoring/logging/health check verified.

Rollback decision window and responsible persons identified.

# 11. Delivery Risks and Controls

| Risk | Control |
| --- | --- |
| Compressed delivery window | Freeze Must scope early; parallelize content/UI/backend; stage-gate nonessential work. |
| Late council content | Create content inventory and owners at Stage 0; use clearly marked non-production fixtures only during development. |
| Translation delays | Build translation model early; permit controlled progressive content completion where Council approves. |
| Generic/template appearance | Enforce Theme 1 skill standard, component inventory and human visual QA. |
| Permission mistakes | Server-side policies, scoped access and negative tests before CMS rollout. |
| Tender/vacancy deadline errors | Store explicit close_at; timezone policy; scheduler plus boundary tests. |
| Legacy SEO loss | Inventory old URLs; redirects; sitemap/canonical verification before launch. |
| Large media/PDFs | Upload limits, validation, optimization, storage policy and CDN/S3 readiness. |
| Deployment failure | Backups, rollback, staging/release candidate and production smoke checklist. |

# 12. Roles and Responsibilities

| Role | Primary accountability |
| --- | --- |
| Project/Product Owner | Scope decisions, prioritization, UAT coordination and sign-off. |
| Technical Lead | Architecture, code quality, security decisions, stage acceptance and release readiness. |
| Backend Developer | Laravel domains/actions/policies/data/workflows/Filament integration. |
| Frontend Developer | React/Inertia implementation, Theme 1 component system, responsive/accessibility behavior. |
| Content Owners | Provide/approve factual council content, translations, imagery and documents. |
| QA | RTM-based verification, regression, E2E, browser/mobile and release evidence. |
| Infrastructure/DevOps | Production environment, CI/CD, backups, workers, scheduler, SSL and monitoring. |

# 13. Final Production GO Criteria

All Must requirements have RTM-linked implementation and verification evidence.

No open Critical or High security/functional release defect.

Production-equivalent MySQL migrations and data constraints verified.

RBAC/scoped access and negative authorization tests pass.

Theme 1 public pages pass human visual, responsive and accessibility review.

Tender/vacancy close behavior and scheduled jobs verified.

SEO metadata, sitemap, redirects and critical legacy URLs verified.

Backup and restore procedure tested; rollback is executable.

Production queues, scheduler, storage, HTTPS and monitoring operational.

UAT acceptance and handover approvals recorded.

# 14. Immediate Next Execution Step

Begin Stage 0/Stage 1 only. Do not implement business modules prematurely. The first coding milestone is a production-ready foundation with Laravel, React, TypeScript, Inertia, Filament, Tailwind, MySQL, Redis, tests and CI working together. Once Stage 1 evidence passes, authorize Stage 2 Identity/Organisation/Security. This sequencing prevents functional development from being built on an unstable foundation.

# 15. Implementation Status Register

| Stage | Status | Owner | Evidence/Reference | Acceptance Date |
| --- | --- | --- | --- | --- |
| Stage 0 | Not Started |  |  |  |
| Stage 1 | Not Started |  |  |  |
| Stage 2 | Not Started |  |  |  |
| Stage 3 | Not Started |  |  |  |
| Stage 4 | Not Started |  |  |  |
| Stage 5 | Not Started |  |  |  |
| Stage 6 | Not Started |  |  |  |
| Stage 7 | Not Started |  |  |  |
| Stage 8 | Not Started |  |  |  |
| Stage 9 | Not Started |  |  |  |
| Stage 10 | Not Started |  |  |  |
| Stage 11 | Not Started |  |  |  |
| Stage 12 | Not Started |  |  |  |
| Stage 13 | Not Started |  |  |  |
| Stage 14 | Not Started |  |  |  |

GOVERNING DELIVERY PLAN - MUTOKO RDC WEBSITE