MUTOKO RURAL DISTRICT COUNCIL

WEBSITE MODERNISATION PROJECT

Formal Software Requirements Specification (SRS)
Requirements Traceability Matrix (RTM)
Production Database Design
Implementation Plan

Version 1.0 • 25 September 2026

Prepared from the supplied Terms of Reference screenshots and the agreed requirements baseline.

# Document Control

| Item | Value |
| --- | --- |
| Document title | Mutoko Rural District Council Website Modernisation – SRS, RTM, Production Database Design and Implementation Plan |
| Version | 1.0 |
| Date | 25 September 2026 |
| Status | Requirements baseline for validation and implementation |
| System type | Public local-authority website + secure CMS/admin portal |
| Primary stakeholders | Council leadership, ICT/web administrators, departmental content owners, finance/procurement/HR/public relations users, residents, businesses, investors, visitors and other public users |
| Proposed implementation stack | Laravel modular application, Filament administration, MySQL 8, Blade/Livewire/Tailwind public frontend, Redis for cache/queues, scheduler/worker processes |
| Languages | English, Shona and Ndebele |
| Delivery baseline | 15 working days: inception 1; development 7; testing/deployment 3; training 1; final documentation 3 |

## Purpose and Interpretation

This document converts the supplied website Terms of Reference into implementable, testable software requirements. Where the screenshots describe a business objective rather than an exact technical mechanism, the SRS expresses the minimum production-grade behaviour needed to satisfy that objective. Items marked as proposed design decisions should be confirmed during inception before development is frozen.

## Contents

1. System Context and Scope

2. Stakeholders, Roles and Permissions

3. Functional Requirements

4. Non-Functional Requirements

5. Business Rules and Workflows

6. Requirements Traceability Matrix

7. Production Database Design

8. Security, Audit and Operations

9. Implementation Plan

10. Testing and Acceptance

11. Deliverables and Handover

12. Assumptions, Risks and Open Decisions

# 1. System Context and Scope

## 1.1 Business Objective

The project will deliver a modern, secure, responsive and maintainable official website for Mutoko Rural District Council. The website will improve public access to council information and services, strengthen transparency, support investment and tourism promotion, publish statutory and operational information, and allow authorised council staff to manage content without requiring source-code changes.

## 1.2 In Scope

Public website with responsive desktop, tablet and mobile layouts.

Secure content management/admin portal with role-based access control.

Council profile, mandate, vision, mission, leadership, departments and organisational information.

Council governance information, policies, by-laws, minutes or other approved governance documents.

Financial transparency content and downloadable approved financial documents.

News, public notices, announcements, events and emergency/important notices.

Tenders/procurement opportunities with opening and closing dates, status and downloadable documents.

Vacancies/careers with opening/closing dates, status and supporting documents.

Projects/development initiatives with status, location, descriptions, media and outcomes.

Investment opportunities, local economic development information and investor-facing content.

Tourism, attractions, heritage and destination information.

Public contact details, offices, map/location information and structured enquiries.

Search, document downloads, SEO metadata, sitemap and analytics.

English, Shona and Ndebele content support.

Legal/privacy/accessibility pages and cookie/analytics disclosures where applicable.

Audit logging, content governance, backups, deployment, training and system documentation.

## 1.3 Out of Scope Unless Approved by Change Control

Online payment gateway or revenue collection.

Full e-services transactional portal for permits, licences or rates accounts.

Native Android/iOS applications.

Automated WhatsApp Business API messaging.

Integration to third-party ERP/financial systems beyond links or agreed data exports.

Citizen identity accounts unless later approved.

## 1.4 Proposed Architecture

A modular monolith is recommended for the initial release: one Laravel application with clear domain modules, a public presentation layer, a Filament administration portal, MySQL for transactional data, Redis for cache/queues, object/file storage abstraction for media and documents, and background workers for scheduled publishing, notifications, indexing and housekeeping. This reduces delivery risk while preserving a clean path to future integrations.

| Layer | Production Design |
| --- | --- |
| Public presentation | Server-rendered Laravel Blade/Livewire/Tailwind; responsive, accessible, SEO-friendly |
| Administration | Filament admin portal with RBAC, approval actions, audit visibility and content lifecycle controls |
| Application | Laravel services/actions, policies, validation, events/jobs and scheduled tasks |
| Data | MySQL 8/InnoDB; UTF8MB4; foreign keys; indexed slugs/status/date fields; soft deletion where appropriate |
| Cache/queues | Redis with supervised workers and retry/dead-letter handling |
| Storage | Laravel filesystem abstraction; local/private object storage in development and S3-compatible/CDN-ready production design |
| Observability | Application logs, audit events, queue failure tracking, uptime/health checks and analytics |

# 2. Stakeholders, Roles and Permissions

| Role | Audience | Core permissions |
| --- | --- | --- |
| Public Visitor | Anonymous | Browse public content, search, download public documents, submit enquiries. |
| System Administrator | Internal | Full configuration, users/roles, system settings, content recovery, audit access. |
| Website Administrator | Internal | Manage website structure, media, content and publication operations. |
| Content Editor | Internal | Create/edit assigned content; submit for approval; cannot approve own governed content where maker-checker is enabled. |
| Content Approver | Internal | Review, approve, reject and publish content within assigned scope. |
| Department Content Owner | Internal | Manage content for an assigned department/module only. |
| Procurement Officer | Internal | Manage tenders/procurement content and documents. |
| HR Officer | Internal | Manage vacancies/careers content. |
| Finance Officer | Internal | Manage approved financial transparency content/documents. |
| Public Relations/Communications | Internal | Manage news, notices, events, public messaging and homepage highlights. |
| Auditor/Read-only Reviewer | Internal | Read published/draft records and audit history without mutation rights. |

# 3. Functional Requirements

| ID | Area | Requirement | Priority |
| --- | --- | --- | --- |
| FR-001 | Public Home Page | The system shall provide a responsive homepage containing configurable hero content, priority notices, council introduction, featured services/information, news, projects, investment/tourism highlights and contact calls-to-action. | Must |
| FR-002 | Council Profile | The system shall publish council mandate, vision, mission, history/profile and approved institutional information. | Must |
| FR-003 | Leadership | The system shall publish leadership profiles with title, biography, photograph, ordering and active/inactive status. | Must |
| FR-004 | Departments | The system shall publish departments/units, responsibilities, contacts and related content. | Must |
| FR-005 | Governance Documents | Authorised users shall upload, classify, version, publish, unpublish and archive governance documents. | Must |
| FR-006 | Financial Transparency | Authorised finance users shall publish approved budgets, financial statements, reports or other transparency documents by reporting period/category. | Must |
| FR-007 | News | Authorised users shall create news articles with title, slug, summary, body, author, category, media, tags, publication status and publication date. | Must |
| FR-008 | Public Notices | The system shall publish time-sensitive notices with effective/expiry dates and priority/featured flags. | Must |
| FR-009 | Events | The system shall publish council/public events with date/time, venue, description, status and optional registration/external link. | Should |
| FR-010 | Tenders | Procurement users shall create tender notices with reference number, title, description, category, issue date, closing date/time, status and downloadable documents. | Must |
| FR-011 | Tender Auto-Close | The system shall automatically mark tenders closed after their configured closing date/time while retaining the public archive. | Must |
| FR-012 | Vacancies | HR users shall publish vacancies with job title, reference, department, location, description, requirements, opening/closing dates and application instructions/link. | Must |
| FR-013 | Vacancy Auto-Close | The system shall automatically close expired vacancies and preserve historical records. | Must |
| FR-014 | Projects | The system shall publish council projects with category, location, status, dates, description, budget visibility flag, progress, media and outcomes. | Must |
| FR-015 | Investment | The system shall publish investment opportunities and investor information with sector/category, location, summary, detailed content, contact/CTA and supporting documents. | Must |
| FR-016 | Tourism | The system shall publish attractions/heritage/tourism content with location, description, media, visitor information and related links. | Must |
| FR-017 | Contact Directory | The system shall display approved office, department, phone, email, physical/postal address, working hours and map information. | Must |
| FR-018 | Public Enquiries | Visitors shall submit structured enquiries containing name, contact details, subject/category, message and consent; staff shall track status and response metadata. | Must |
| FR-019 | Spam Protection | Public forms shall implement server-side validation, rate limiting and anti-spam controls. | Must |
| FR-020 | Site Search | Users shall search published pages, news, notices, tenders, vacancies, projects and documents using keywords and filters. | Must |
| FR-021 | Media Library | Authorised users shall upload and reuse images/files with title, alt text, caption, MIME validation, size limits and ownership metadata. | Must |
| FR-022 | Document Downloads | The system shall expose approved public documents through stable URLs and record aggregate download events/metrics where enabled. | Should |
| FR-023 | Multilingual Content | Content types designated for translation shall support English, Shona and Ndebele without duplicating core business records. | Must |
| FR-024 | Language Switching | Public users shall switch language while remaining on the equivalent page when a translation exists; otherwise the configured fallback shall be used. | Must |
| FR-025 | CMS Drafts | Content shall support draft state before publication. | Must |
| FR-026 | Review/Approval | Governed content shall support submit-for-review, approve, reject with reason, publish and archive transitions. | Must |
| FR-027 | Scheduled Publishing | Authorised users shall schedule future publication and optional expiry/unpublication. | Should |
| FR-028 | Preview | Editors/approvers shall preview unpublished content securely before publication. | Should |
| FR-029 | Revision History | The system shall preserve meaningful content revisions and identify who changed what and when. | Must |
| FR-030 | RBAC | The administration portal shall enforce server-side role and permission checks for every protected resource/action. | Must |
| FR-031 | Scoped Access | Department/module users shall only access records within their assigned content scope unless granted broader permission. | Must |
| FR-032 | Audit Trail | The system shall record security and business audit events for login, user/role changes, content lifecycle changes, document actions and critical configuration changes. | Must |
| FR-033 | SEO Metadata | Editors shall manage page title, meta description, canonical URL, social image and index/no-index controls for eligible content. | Must |
| FR-034 | Sitemap/Robots | The system shall generate and maintain XML sitemap and robots directives from published content. | Must |
| FR-035 | Redirects | Administrators shall maintain 301 redirects for changed/legacy URLs to protect indexed links and avoid unnecessary 404s. | Must |
| FR-036 | Analytics | The site shall support privacy-conscious web analytics for visits, popular pages, traffic sources and downloads without exposing admin data. | Should |
| FR-037 | Legal Pages | The system shall publish privacy, terms/disclaimer, accessibility and other approved legal notices. | Must |
| FR-038 | Global Settings | Administrators shall manage council identity, logos, social links, contact details, default SEO values, language settings and footer content. | Must |
| FR-039 | Homepage Curation | Authorised users shall select/order featured news, notices, projects, tourism and investment items without code changes. | Should |
| FR-040 | Content Relationships | Editors shall link related departments, documents, projects, news and other content for contextual navigation. | Should |

# 4. Non-Functional Requirements

| ID | Category | Requirement |
| --- | --- | --- |
| NFR-001 | Security | All production traffic shall use HTTPS; secure cookies, CSRF protection, output escaping, validation, least privilege and security headers shall be enabled. |
| NFR-002 | Authentication | Admin access shall require authenticated accounts; password hashing, login throttling, reset controls and configurable MFA for privileged users shall be supported. |
| NFR-003 | Availability | The production service should target at least 99.5% monthly availability excluding planned maintenance. |
| NFR-004 | Performance | Typical public pages should achieve server response suitable for Core Web Vitals targets; cached public pages should normally render without database-heavy repeated queries. |
| NFR-005 | Scalability | Application services shall be stateless where practical; cache, queues and file storage shall allow horizontal scaling without redesign. |
| NFR-006 | Accessibility | Public templates shall target WCAG 2.1 AA: keyboard operation, semantic headings, labels, focus visibility, colour contrast and meaningful alt text. |
| NFR-007 | Responsive Design | All public pages and public forms shall operate on common mobile, tablet and desktop viewport sizes. |
| NFR-008 | Browser Support | Current stable Chrome, Edge, Firefox and Safari shall be supported; graceful degradation shall apply to older browsers. |
| NFR-009 | SEO | Public pages shall use crawlable URLs, semantic markup, canonical metadata, sitemap, structured metadata where appropriate and controlled redirects. |
| NFR-010 | Maintainability | Code shall follow framework conventions, modular boundaries, automated formatting/static checks and documented deployment/configuration. |
| NFR-011 | Auditability | Critical admin actions shall produce attributable audit events containing actor, action, target, timestamp and relevant before/after metadata. |
| NFR-012 | Backup/Recovery | Automated database and file backups shall be scheduled, encrypted/protected, retention-controlled and periodically restore-tested. |
| NFR-013 | Privacy | Only necessary personal information shall be collected; enquiry data shall have controlled access and defined retention. |
| NFR-014 | Data Integrity | Foreign keys, uniqueness rules, validation, transactions and controlled state transitions shall prevent invalid business states. |
| NFR-015 | Localization | The database and frontend shall support UTF-8/UTF8MB4 and translated content without corrupting local-language characters. |
| NFR-016 | Observability | Production shall provide application/error logs, failed-job visibility, health checks and alertable operational signals. |
| NFR-017 | Deployment | Deployment shall be repeatable with environment-specific configuration, migrations, cache rebuilds, worker restarts and rollback procedure. |
| NFR-018 | Content Portability | Documents/media shall use a storage abstraction rather than hard-coded local paths, enabling later S3/CDN migration. |

# 5. Business Rules and Workflows

## 5.1 Content Publication Lifecycle

Editor creates or updates content in Draft.

Editor validates required language/content/media/SEO fields and submits for review.

Approver reviews the proposed version.

Approver either rejects with a reason or approves.

Approved content is published immediately or at the scheduled time.

Any expiry date triggers automatic unpublication/closure where applicable.

Subsequent edits create a new revision while the published version remains attributable in history.

Archive removes content from active listings without destroying audit history.

## 5.2 Tender Lifecycle

Draft → Review → Published/Open → Closed → Awarded/Archived. Closing date/time is mandatory for open tenders. The scheduler must close an open tender once the deadline is reached. Changes to deadline or tender documents after publication must be audited.

## 5.3 Vacancy Lifecycle

Draft → Review → Published/Open → Closed → Archived. Expiry is controlled by closing date/time. The public website must not present expired vacancies as open.

## 5.4 Translation Rule

Business records such as tender reference numbers, project status and dates remain language-neutral. Translatable fields are stored in translation records keyed by locale. English may be configured as the default/fallback, while Shona and Ndebele translations can be progressively completed.

## 5.5 URL and SEO Rule

Published content receives stable slugs. Slug changes must create or require a permanent redirect from the previous public URL. Deleted or archived content should return an intentional response or redirect rather than silently breaking indexed URLs.

# 6. Requirements Traceability Matrix (RTM)

| Req ID | Area | Pri. | Module | Primary data | Test ID | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| FR-001 | Public Home Page | Must | CMS / Site Structure | pages, page_translations, site_settings, menus, menu_items | TC-001 | UAT + automated test |
| FR-002 | Council Profile | Must | CMS / Site Structure | pages, page_translations, site_settings, menus, menu_items | TC-002 | UAT + automated test |
| FR-003 | Leadership | Must | CMS / Site Structure | pages, page_translations, site_settings, menus, menu_items | TC-003 | UAT + automated test |
| FR-004 | Departments | Must | CMS / Site Structure | pages, page_translations, site_settings, menus, menu_items | TC-004 | UAT + automated test |
| FR-005 | Governance Documents | Must | Documents / Media | documents, document_versions, media_assets, download_events | TC-005 | UAT + automated test |
| FR-006 | Financial Transparency | Must | Documents / Media | documents, document_versions, media_assets, download_events | TC-006 | UAT + automated test |
| FR-007 | News | Must | Communications | posts, post_translations, categories, tags, post_tag | TC-007 | UAT + automated test |
| FR-008 | Public Notices | Must | Communications | posts, post_translations, categories, tags, post_tag | TC-008 | UAT + automated test |
| FR-009 | Events | Should | Communications | posts, post_translations, categories, tags, post_tag | TC-009 | UAT + automated test |
| FR-010 | Tenders | Must | Procurement | tenders, tender_translations, tender_documents | TC-010 | UAT + automated test |
| FR-011 | Tender Auto-Close | Must | Procurement | tenders, tender_translations, tender_documents | TC-011 | UAT + automated test |
| FR-012 | Vacancies | Must | Careers | vacancies, vacancy_translations | TC-012 | UAT + automated test |
| FR-013 | Vacancy Auto-Close | Must | Careers | vacancies, vacancy_translations | TC-013 | UAT + automated test |
| FR-014 | Projects | Must | Projects | projects, project_translations, project_media | TC-014 | UAT + automated test |
| FR-015 | Investment | Must | Investment | investment_opportunities, investment_translations | TC-015 | UAT + automated test |
| FR-016 | Tourism | Must | Tourism | tourism_items, tourism_translations, media_assets | TC-016 | UAT + automated test |
| FR-017 | Contact Directory | Must | Contact / Enquiries | contact_points, enquiries, enquiry_events | TC-017 | UAT + automated test |
| FR-018 | Public Enquiries | Must | Contact / Enquiries | contact_points, enquiries, enquiry_events | TC-018 | UAT + automated test |
| FR-019 | Spam Protection | Must | Contact / Enquiries | contact_points, enquiries, enquiry_events | TC-019 | UAT + automated test |
| FR-020 | Site Search | Must | Search | search index / published content | TC-020 | UAT + automated test |
| FR-021 | Media Library | Must | Documents / Media | documents, document_versions, media_assets, download_events | TC-021 | UAT + automated test |
| FR-022 | Document Downloads | Should | Documents / Media | documents, document_versions, media_assets, download_events | TC-022 | UAT + automated test |
| FR-023 | Multilingual Content | Must | Localization | *_translations, locales | TC-023 | UAT + automated test |
| FR-024 | Language Switching | Must | Localization | *_translations, locales | TC-024 | UAT + automated test |
| FR-025 | CMS Drafts | Must | Editorial Workflow | content_revisions, approval_requests, approval_steps | TC-025 | UAT + automated test |
| FR-026 | Review/Approval | Must | Editorial Workflow | content_revisions, approval_requests, approval_steps | TC-026 | UAT + automated test |
| FR-027 | Scheduled Publishing | Should | Editorial Workflow | content_revisions, approval_requests, approval_steps | TC-027 | UAT + automated test |
| FR-028 | Preview | Should | Editorial Workflow | content_revisions, approval_requests, approval_steps | TC-028 | UAT + automated test |
| FR-029 | Revision History | Must | Editorial Workflow | content_revisions, approval_requests, approval_steps | TC-029 | UAT + automated test |
| FR-030 | RBAC | Must | Identity / Governance | users, roles, permissions, user_scopes, audit_events | TC-030 | UAT + automated test |
| FR-031 | Scoped Access | Must | Identity / Governance | users, roles, permissions, user_scopes, audit_events | TC-031 | UAT + automated test |
| FR-032 | Audit Trail | Must | Identity / Governance | users, roles, permissions, user_scopes, audit_events | TC-032 | UAT + automated test |
| FR-033 | SEO Metadata | Must | SEO / Analytics | seo_metadata, redirects, analytics/download events | TC-033 | UAT + automated test |
| FR-034 | Sitemap/Robots | Must | SEO / Analytics | seo_metadata, redirects, analytics/download events | TC-034 | UAT + automated test |
| FR-035 | Redirects | Must | SEO / Analytics | seo_metadata, redirects, analytics/download events | TC-035 | UAT + automated test |
| FR-036 | Analytics | Should | SEO / Analytics | seo_metadata, redirects, analytics/download events | TC-036 | UAT + automated test |
| FR-037 | Legal Pages | Must | CMS / Site Structure | pages, page_translations, site_settings, menus, menu_items | TC-037 | UAT + automated test |
| FR-038 | Global Settings | Must | CMS / Site Structure | pages, page_translations, site_settings, menus, menu_items | TC-038 | UAT + automated test |
| FR-039 | Homepage Curation | Should | CMS / Site Structure | pages, page_translations, site_settings, menus, menu_items | TC-039 | UAT + automated test |
| FR-040 | Content Relationships | Should | CMS Core | content relationships / settings | TC-040 | UAT + automated test |

# 7. Production Database Design

## 7.1 Database Standards

MySQL 8.0+, InnoDB, utf8mb4 and a consistent Unicode collation.

Use bigint or ULID/UUID primary identifiers consistently; public identifiers must not expose sequential business assumptions.

All foreign keys explicitly constrained; delete behaviour chosen per domain (restrict, cascade for pure child rows, or set null where historical retention is required).

created_at/updated_at on mutable entities; deleted_at for recoverable content where soft deletion is appropriate.

Use UTC for stored timestamps; render in configured local timezone.

Money uses DECIMAL, never floating point. Dates and deadlines use DATE/DATETIME as appropriate.

JSON only for genuinely flexible metadata, not as a substitute for relational modelling.

Indexes on foreign keys, status, slug, locale, publication/closing dates and common listing/filter columns.

Unique constraints for slugs within their namespace, reference numbers, role/permission names and translation (parent_id, locale).

Audit events and revisions are append-oriented and must not be silently overwritten.

## 7.2 Core Entity Catalogue

| Table / Aggregate | Purpose | Key fields |
| --- | --- | --- |
| users | Admin identities | id, name, email, password, status, last_login_at, mfa fields, timestamps |
| roles / permissions | RBAC definitions | id, name, guard; pivots role_permission, user_role |
| user_scopes | Department/module scope | user_id, scope_type, scope_id |
| departments | Council organisational units | id, name, slug, description, contacts, status |
| locales | Supported languages | code (en/sn/nd), name, is_default, is_active |
| pages | Generic institutional/legal pages | id, type, slug, status, published_at, author/approver |
| page_translations | Translated page content | page_id, locale, title, summary, body |
| posts | News/notices/events | id, type, category_id, slug, status, featured, starts_at, ends_at, published_at |
| post_translations | Translated post content | post_id, locale, title, summary, body |
| categories / tags | Taxonomy | id, type, name, slug; post_tag pivot |
| documents | Logical public/internal document | id, category, title, visibility, status, current_version_id |
| document_versions | Immutable file versions | document_id, version_no, storage_disk/path, filename, mime, size, checksum, uploaded_by |
| media_assets | Reusable media library | id, disk/path, mime, size, width/height, alt_text, caption, checksum |
| tenders | Procurement notice | id, reference_no, category_id, issue_at, close_at, status, published_at |
| tender_translations | Tender narrative fields | tender_id, locale, title, summary, description |
| tender_documents | Tender/document link | tender_id, document_id, type, sort_order |
| vacancies | Job opportunities | id, reference_no, department_id, location, open_at, close_at, status |
| vacancy_translations | Translated job text | vacancy_id, locale, title, description, requirements, application_instructions |
| projects | Development projects | id, department_id, category_id, location, start/end dates, status, progress_percent, budget fields/visibility |
| project_translations | Project narrative | project_id, locale, title, summary, description, outcomes |
| investment_opportunities | Investor content | id, sector/category, location, status, contact fields, published_at |
| investment_translations | Investor narrative | investment_id, locale, title, summary, body |
| tourism_items | Attractions/heritage | id, category, location, geo fields, status, published_at |
| tourism_translations | Tourism narrative | tourism_id, locale, name, summary, description, visitor_info |
| contact_points | Published contacts | id, department_id, type, label, phone/email/address, hours, map/geo, is_public |
| enquiries | Public submissions | id/public_id, category, name, email, phone, subject, message, consent_at, status, assigned_to |
| enquiry_events | Enquiry history | enquiry_id, actor_id, event_type, note, created_at |
| content_revisions | Revision snapshots | content_type, content_id, revision_no, payload/hash, actor_id, created_at |
| approval_requests | Governed publication request | content_type/id, submitted_by, status, submitted_at, completed_at |
| approval_steps | Review decision history | approval_request_id, step/order, approver_id, decision, reason, decided_at |
| seo_metadata | SEO values | content_type/id, locale, title, description, canonical_url, social_image_id, robots flags |
| redirects | Legacy/permanent redirects | source_path unique, target_url/path, status_code, active, hits |
| download_events | Download analytics | document_id/version_id, session/ip hash, user_agent summary, created_at |
| audit_events | Security/business audit | actor_id, event, auditable_type/id, before_json, after_json, ip_hash, correlation_id, created_at |
| site_settings | Typed global settings | key unique, value, type, group, updated_by |
| menus / menu_items | Navigation | menu location; nested items, labels/translations, URLs/content refs, order, visibility |
| jobs / failed_jobs | Queue infrastructure | framework queue tables where database queue fallback is used |

## 7.3 Key Relationships

Department 1—N Vacancies, Projects and Contact Points.

Page/Post/Tender/Vacancy/Project/Investment/Tourism 1—N Translation records.

Document 1—N Document Versions; the document points to the current approved version.

Tender N—M Documents through tender_documents.

Post N—M Tags; Post N—1 Category.

Any governed content 1—N Revisions and 1—N Approval Requests through polymorphic references.

Any publishable content 1—1 or 1—N localized SEO metadata.

User N—M Roles; Role N—M Permissions; User 1—N scoped grants.

Enquiry 1—N Enquiry Events; optional assignment to an internal User.

Audit Events polymorphically reference critical business records.

## 7.4 Critical Constraints and Indexes

| Object | Constraint / Index |
| --- | --- |
| translations | UNIQUE(parent_id, locale); locale FK to locales.code |
| tenders | UNIQUE(reference_no); INDEX(status, close_at); CHECK close_at > issue_at where supported/validated |
| vacancies | UNIQUE(reference_no) when reference supplied; INDEX(status, close_at) |
| pages/posts | UNIQUE slug in applicable route namespace; INDEX(status, published_at) |
| redirects | UNIQUE(source_path); INDEX(active, status_code) |
| documents | INDEX(category, status, visibility); document_versions UNIQUE(document_id, version_no) |
| projects | INDEX(status, department_id, published_at); progress range 0..100 |
| enquiries | INDEX(status, category, created_at, assigned_to); public_id UNIQUE |
| audit_events | INDEX(actor_id, created_at); INDEX(auditable_type, auditable_id, created_at); correlation_id indexed |
| approval_requests | INDEX(content_type, content_id, status); prohibit invalid simultaneous active requests at service layer/constraint strategy |

## 7.5 Data Retention and Deletion

Public content may be soft-deleted to support recovery, but audit events, publication decisions and historical document versions should follow an append/retention policy. Enquiries contain personal information and require a documented retention period. Backups must follow a separate retention schedule and cannot be treated as a substitute for application-level audit history.

# 8. Security, Audit and Production Operations

Separate public and administration route groups; admin routes never rely on hidden UI controls for authorization.

Use policy/gate enforcement and least-privilege permissions for create, update, delete, approve, publish, manage users, manage roles and view audit.

Privileged roles should use MFA and stronger session controls.

File uploads must validate MIME/type/size, generate safe storage names and prevent executable upload exposure.

Private/unpublished documents must be served through authorised application routes or signed URLs, not predictable public paths.

Use CSRF protection, output escaping, prepared ORM queries, rate limiting and security headers.

Store secrets only in environment/secret management; never commit production credentials.

Audit user/role changes, authentication events, publishing decisions, tender/vacancy deadline changes, redirects and system settings.

Daily automated backups recommended, with periodic restore drills and documented RPO/RTO agreed during inception.

Queue workers and scheduler must be supervised in production; failed jobs must be visible and retryable.

Production release requires database migration backup/rollback plan, health check, smoke tests and post-deployment verification.

# 9. Implementation Plan

## 9.1 Delivery Strategy

The Terms of Reference baseline indicates a 15-working-day delivery window. To make that schedule achievable, requirements must be frozen at inception, content owners must provide source material promptly, and the team should use a proven Laravel/Filament foundation rather than build CMS infrastructure from scratch.

| Time | Workstream | Activities | Exit output |
| --- | --- | --- | --- |
| Day 1 | Inception & requirements freeze | Confirm information architecture, content inventory, roles, language strategy, hosting/domain/SSL, acceptance criteria, brand assets, migration/redirect needs. | Signed requirements baseline; architecture and content map. |
| Days 2–3 | Foundation | Repository, environments, Laravel foundation, auth/RBAC, locales, settings, media/documents, audit, base design system, navigation. | Secure working skeleton; CI checks; DB migrations. |
| Days 4–5 | Core CMS & institutional content | Pages, leadership, departments, governance, financial documents, news/notices/events, revisions and approval workflow. | Core public pages + admin CRUD/workflow. |
| Days 6–7 | Opportunity modules | Tenders with auto-close, vacancies with auto-close, projects, investment, tourism. | Functional domain modules and public listings/details. |
| Day 8 | Contact, search & SEO | Contacts, enquiry form, spam controls, search, SEO metadata, sitemap, redirects, analytics hooks. | Discoverability and public interaction complete. |
| Day 9 | Multilingual & responsive completion | Translation UI, fallback rules, language switcher, mobile/tablet refinement, accessibility pass. | English/Shona/Ndebele-ready responsive site. |
| Day 10 | Content loading & integration hardening | Load approved priority content, optimise media, verify links/documents, configure storage/cache/queues. | UAT-ready staging build. |
| Days 11–12 | QA/UAT | Functional tests, permissions, workflow tests, accessibility, responsive/browser tests, security checks, performance and content validation. | Defect register; UAT fixes. |
| Day 13 | Production deployment | Backup, production config, DB migration, storage, workers, scheduler, SSL/security headers, analytics, sitemap/Search Console readiness, smoke tests. | Production release candidate/live deployment. |
| Day 14 | Training | Admin/editor/approver training; publishing, tenders, vacancies, translations, documents, audit and basic support. | Training session and admin guide. |
| Day 15 | Final documentation & handover | Final SRS/RTM, architecture/database notes, deployment/runbook, user guide, credentials handover process, source code and acceptance pack. | Handover and sign-off package. |

## 9.2 Work Breakdown Structure

| WBS | Workstream | Scope |
| --- | --- | --- |
| WBS-01 | Discovery | Requirements validation, stakeholders, content inventory, site map, acceptance criteria |
| WBS-02 | UX/UI | Responsive templates, navigation, component library, accessibility patterns |
| WBS-03 | Platform | Laravel setup, environments, CI, configuration, logging, queues, scheduler |
| WBS-04 | Identity | Authentication, users, roles, permissions, scoped access, MFA readiness |
| WBS-05 | CMS Core | Pages, menus, settings, media, documents, translations, revisions, approval |
| WBS-06 | Communications | News, notices, events, homepage curation |
| WBS-07 | Procurement | Tenders, documents, deadlines, auto-close, archive |
| WBS-08 | Careers | Vacancies, deadlines, auto-close, archive |
| WBS-09 | Development | Projects and development initiatives |
| WBS-10 | Economic Promotion | Investment and tourism content |
| WBS-11 | Public Interaction | Contact directory, enquiries, anti-spam |
| WBS-12 | Discoverability | Search, SEO, sitemap, robots, redirects, analytics |
| WBS-13 | QA | Automated tests, UAT, security, accessibility, browser/mobile, performance |
| WBS-14 | Release | Production infrastructure, backups, deployment, monitoring, smoke tests |
| WBS-15 | Handover | Training, manuals, runbook, source code, acceptance documentation |

## 9.3 Definition of Done

Requirement has implemented server-side behaviour and user interface where applicable.

Authorization is enforced and negative permission tests pass.

Validation and business rules are implemented.

Database migrations and indexes exist and can run on a clean production-equivalent database.

Automated tests cover critical happy paths and failure paths.

Responsive and accessibility checks pass for affected public pages.

Audit event exists for governed/critical actions.

Documentation is updated and no Critical/High severity defect remains open for release.

# 10. Testing and Acceptance

| Test ID | Acceptance area | Acceptance condition |
| --- | --- | --- |
| AT-001 | Public navigation | All approved primary menu routes load without broken links on mobile and desktop. |
| AT-002 | Content workflow | Editor cannot publish governed content directly; approver can approve/publish; rejection reason is retained. |
| AT-003 | Tender deadline | Open tender automatically becomes closed at configured closing time and is no longer shown as open. |
| AT-004 | Vacancy deadline | Expired vacancy automatically closes and remains available only according to archive rules. |
| AT-005 | Translations | Equivalent English/Shona/Ndebele records display correctly; fallback is deterministic when translation is absent. |
| AT-006 | Permissions | Users cannot access unauthorised admin resources by URL or crafted request. |
| AT-007 | Documents | Approved files download successfully; disallowed file types/private files cannot be exposed. |
| AT-008 | Enquiries | Valid enquiry persists; invalid/spam/rate-limited submissions are rejected safely. |
| AT-009 | SEO | Published content has canonical metadata; sitemap contains eligible pages; redirect rules return 301 correctly. |
| AT-010 | Responsive | Key templates pass agreed mobile/tablet/desktop viewport checks. |
| AT-011 | Accessibility | Keyboard navigation, labels, headings, focus, alt text and contrast meet the agreed WCAG 2.1 AA acceptance checks. |
| AT-012 | Backup/restore | A production-equivalent backup can be restored and application smoke tests pass. |
| AT-013 | Audit | Critical admin actions are attributable to actor, target and timestamp. |
| AT-014 | Performance | Representative public pages meet agreed staging performance thresholds under realistic content. |
| AT-015 | Production smoke | Homepage, admin login, content publish, tender/vacancy listing, search, enquiry, documents and language switch pass after deployment. |

# 11. Deliverables and Handover

Production-ready source code and database migrations.

Configured public website and secure administration portal.

Responsive UI templates and reusable component/design system.

Configured content types/modules described in this SRS.

Initial approved content population/migration as agreed during inception.

Production deployment configuration and environment checklist.

Database schema/design documentation and backup/restore procedure.

SRS and Requirements Traceability Matrix.

Administrator/editor user guide and training material.

Technical deployment/operations runbook.

Test evidence/UAT register and release checklist.

Source code handover and controlled credentials/ownership transfer.

# 12. Assumptions, Risks and Open Decisions

| Type | Item | Required action |
| --- | --- | --- |
| Assumption | Council supplies approved text, images, logos, documents and translations on time. | Assign content owners on Day 1 and freeze priority content list. |
| Assumption | Hosting supports PHP/Laravel, MySQL, SSL, scheduler and long-running/supervised queue workers or an agreed equivalent. | Validate hosting during inception. |
| Risk | 15 working days is compressed for a production public-sector site. | Freeze scope; prioritise Must requirements; parallelise content preparation and QA. |
| Risk | Incomplete Shona/Ndebele translations can delay multilingual acceptance. | Implement translation-ready architecture first; agree which content must be fully translated at launch. |
| Risk | Legacy URLs may already be indexed by search engines. | Create a redirect inventory and preserve high-value URLs with 301 mappings. |
| Risk | Large PDFs/images can harm performance and storage. | Set upload limits, compression rules and document/media standards. |
| Risk | Content publication without governance can create reputational/legal issues. | Use role separation, approvals, revision history and audit logs. |
| Open decision | Exact RPO/RTO and backup retention. | Approve during infrastructure review. |
| Open decision | Whether MFA is mandatory for all admins or only privileged roles. | Approve security baseline at inception. |
| Open decision | Exact analytics platform and consent requirements. | Confirm privacy/legal preference before production. |
| Open decision | Whether public project budgets/financial figures are displayed at record level. | Finance/council to define visibility policy. |
| Open decision | Exact content requiring maker-checker approval versus direct publication. | Create content-governance matrix on Day 1. |

# Appendix A – Recommended Module Boundaries

| Module | Responsibilities |
| --- | --- |
| Identity & Access | Users, roles, permissions, scopes, authentication, privileged access |
| Organisation | Departments, leadership, contacts |
| CMS Core | Pages, menus, site settings, translations, content relationships |
| Editorial Governance | Revisions, approvals, publishing, scheduling, archive |
| Media & Documents | Media library, document versions, file validation, downloads |
| Communications | News, notices, events, homepage highlights |
| Procurement | Tenders, tender documents, closing rules |
| Careers | Vacancies and closing rules |
| Projects | Council development projects and progress |
| Investment | Investor-facing opportunities/content |
| Tourism | Attractions, heritage and visitor information |
| Engagement | Contact forms/enquiries and handling history |
| SEO & Discovery | Search, metadata, sitemap, robots, redirects, analytics |
| Audit & Operations | Audit events, logs, queues, scheduler, backups/health checks |

# Appendix B – Release Gate

The production release is GO only when all Must requirements planned for the release are traceable to implemented modules and test evidence; no Critical or High security/functional defect remains open; production backups and rollback are verified; admin authorization has negative tests; public mobile/accessibility checks pass; SSL, scheduler and queue workers are operational; and council UAT/sign-off is recorded.